## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| AnaCondo | - | 2024-01-23 | 2024-05-01 |  | 10% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 4 | 2024-01-23 | 2024-02-07 | 15 | Complete
| 101 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07 | 15 | Complete
| 102 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07 | 15 | Complete
| Sprint 2 |  |  | 30 | 2024-02-08 | 2024-02-28 | 20 | In Progress
| 103 | Create Account/Login | Suha A. | 2 | 2024-02-08 | 2024-02-20 | 12 | In Progress
| 104 | Create Account/Login | Sofia V. | 2 | 2024-02-08 | 2024-02-20 | 12 | In Progress
| 105 | Create Account/Login | Inas F. | 2 | 2024-02-08 | 2024-02-20 | 12 | Not Started
| 106 | Dashboard | Cosmin S. | 8 | 2024-02-08 | 2024-02-28 | 20 | Not Started
| 107 | Create Account/Login | Jason N. | 3 | 2024-02-08 | 2024-02-28 | 20 | Not Started
| 208 | Upload files | Ryan S. | 3 | 2024-02-08 | 2024-02-20 | 12 | Not Started
| 209 | Create and Modify Property | Megan C. | 5 | 2024-02-08 | 2024-02-28 | 20 | Not Started
| 310 | Send keys | Cleopatr-Aliak M. | 5 | 2024-02-08 | 2024-02-28 | 20 | Not Started
| Sprint 3 |  |  | 19 | 2024-02-29 | 2024-03-21 | 21 | Not Started
| 511 | Reserve Common Facility | Sisahga P. | 8 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| 512 | Setting up common facility | Sana A. | 5 | 2024-02-29 | 2024-10-10 | 224 | Not Started
| 713 | Public user notifications | Ryan S. | 3 | 2024-03-11 | 2024-10-21 | 224 | Not Started
| 615 | Organize events through portal | Jason N. | 3 | 2024-02-29 | 2024-10-10 | 224 | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9