## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| AnaCondo | - | 2024-01-23 | 2024-05-01 |  | 10% |  | SCOPE STATEMENT
AT RISK | TASK NAME | TASK DESCRIPTION / FEATURES | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  | 4 | 2024-01-23 | 2024-02-07 | 15 | Complete
| 101 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07 | 15 | Complete
| 102 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07 | 15 | Complete
| Sprint 2 |  |  | 39 | 2024-02-08 | 2024-02-28 | 20 | In Progress
| 103 | Condo Owner Account | Suha A. | 2 | 2024-02-08 | 2024-02-25 | 17 | Completed
| 104 | Create Account/Login & dashboard (Rental Users) | Sofia V. | 4 | 2024-02-08 | 2024-02-25 | 17 | Completed
| 105 | Create Account/Login & dashboard (Employee) | Inas F. | 4 | 2024-02-08 | 2024-02-25 | 17 | In Progress
| 106 | Dashboard Properties (Responsive Front-End) | Cosmin S. | 7 | 2024-02-08 | 2024-02-28 | 20 | Completed
| 107 | Create Account/Login & dashboard (Management) | Jason N. | 4 | 2024-02-08 | 2024-02-25 | 17 | Completed
| 209 | Create and Modify Property Information | Megan C. | 5 | 2024-02-08 | 2024-02-28 | 20 | In Progress
| 208 | Upload files properties | Sisahga | 3 | 2024-02-08 | 2024-02-25 | 17 | In Progress
|  | Testing | Ryan | 10 | 2024-02-25 | 2024-04-03 | 38 | Completed
| Sprint 3 |  |  | 50 | 2024-02-29 | 2024-03-13 | 13 | Not Started
| 103 | Condo Owner Account | Suha A. | 2 | 2024-02-29 | 2024-03-09 | 9 | In Progress
| 511 | Reserving Facility | Sisahga | 8 | 2024-02-29 | 2024-03-13 | 13 | Not Started
| 512 | Setting Up a Common Facility | Sisahga | 4 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| 713 | Public User Notifications |  | 3 | 2024-02-29 | 2024-03-15 | 15 | Not Started
| 614 | Message Board | Ryan | 3 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| 615 | Organize Events Through Portal |  | 3 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| 316 | Discount Offers | Suha A. | 4 | 2024-02-29 | 2024-03-18 | 18 | Not Started
| 717 | Request Submissions |  | 3 | 2024-02-29 | 2024-03-19 | 19 | Not Started
| 318 | Request Assignment |  | 6 | 2024-02-29 | 2024-03-19 | 19 | Not Started
| 319 | Employee Roles |  | 3 | 2024-02-29 | 2024-03-19 | 19 | Not Started
| 620 | Employee Notifications |  | 3 | 2024-02-29 | 2024-03-19 | 19 | Not Started
|  | Testing |  | 10 | 2024-02-25 | 2024-04-03 | 38 | Not Started
| Sprint 4 |  |  | 42 | 2024-03-14 | 2024-03-27 | 13 | Not Started
| 621 | Employee Request Completion |  | 10 | 2024-03-14 | 2024-04-03 | 20 | Not Started
| 422 | Generate Annual finance report |  | 3 | 2024-02-08 | 2024-02-25 | 17 | Not Started
| 423 | Setting Condo Unit Costs |  | 3 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| 424 | Calculate Condo Fees |  | 2 |  |  |  | Not Started
| 425 | Calculate Operation costs |  | 2 |  |  |  | Not Started
| 26 | Implementing App on Multiple Platforms |  | 20 | 2024-03-14 | 2024-04-03 |  | Not Started
|  | Testing |  | 2 | 2024-02-29 | 2024-03-10 | 10 | Not Started
| Sprint 5 |  |  | 30 | 2024-03-28 | 2024-04-10 | 13 | Not Started
| 26 | Implementing App on Multiple Platforms |  | 20 | 2024-03-14 | 2024-04-03 |  | Not Started
|  | Testing |  | 10 | 2024-02-25 | 2024-04-07 |  | Not Started

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 |  |  |  | 2024-02-05 | 2024-02-20
| 101 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07
| 102 | Create Account/Login | Suha A., Ryan S., Sisahga P. | 2 | 2024-01-23 | 2024-02-07
| Sprint 2 |  |  |  | 2024-02-08 | 2024-02-28
| 103 |  |  |  | 2024-02-08 | 2024-02-28
| 104 |  |  |  | 2024-02-08 | 2024-02-28
| 105 |  |  |  | 2024-02-08 | 2024-02-28
| 106 |  |  |  | 2024-02-08 | 2024-02-28
| 107 |  |  |  | 2024-02-08 | 2024-02-28
| 209 |  |  |  | 2024-02-08 | 2024-02-28
| 208 |  |  |  | 2024-02-08 | 2024-02-28
Sprint 3
Feature 7
Feature 8
Feature 9